## 132 KV INSULATORS
CONTRACT FOR COMPLETION OF NANYUKI - ISIOLO 132KV TRANSMISSION LINE: KETRACO/PT/007/2021
CLIENT: KETRACO
CONTRACTOR: BURHANI ENGINEERS LIMITED
DOCUMENT NAME: APPENDIX 1B.REV 1 132KV INSULATORS AND CONDUCTOR ACCESSORIES
INSULATORS AND ACCESSORIES FOR MULT-CIRCUIT SCOPE
| SL. No. | Tower No. | Tower Type |  | Insulator | [5 empty] | Conductor Accesorries
|  |  |  | SPAN AHEAD | Single Suspension Insulator | Double Suspension Insulator | Single Tension Insulator | Double Tension Insulator | V Suspension Insulator | Jumper Insulator | Midspan Joints | Vibration Damper | Repair Sleeve
|  |  |  | METRES | Nos. | Nos. | Nos. | Nos. |  |  | Sets | Nos. | Nos.
| 1 | GANTRY | GANTRY |  |  |  | 9
28
| 2 | 1 | 3HT |  |  |  | 18 |  |  | 9 |  | 18
209
| 3 | 2 | 3HT |  |  |  | 18 |  |  | 9 |  | 18
325
| 4 | 3 | 3S |  |  | 6 |  |  | 12 |  |  | 18
322
| 5 | 4 | 3S |  |  | 6 |  |  | 12 |  |  | 18
338
| 6 | 5 | 3S |  | 3 |  |  |  | 12 |  |  | 18
328
| 7 | 6 | 3S |  | 3 |  |  |  | 12 |  |  | 18
295.5
3 | 8 | 7 | 3HT |  |  |  | 9 |  |  |  |  | 9
|  |  |  | 1845.5 | 6 | 12 | 54 | 0 | 48 | 18 | 0 | 117 | 0
INSULAORS NEEDED
138
FOR SINGLE CIRCUIT SCOPE
| SL. No. | Tower No. | Tower Type |  | Insulator | [5 empty] | Conductor Accesorries
|  |  |  | SPAN AHEAD | Single Suspension Insulator | Double Suspension Insulator | Single Tension Insulator | Double Tension Insulator | V Suspension Insulator | Jumper Insulator | Midspan Joints | Vibration Damper | Repair Sleeve
|  |  |  | METRES | Nos. | Nos. | Nos. | Nos. |  |  | Sets | Nos. | Nos.
| 9 | 21 | H+0 |  |  |  | 3 |  |  |  |  | 3
245
| 10 | 21A | S+3 |  |  | 6 | [5 empty] | 6
| 11 |  |  | 192
|  | 21B | M+0 |  |  |  | 6 |  |  |  |  | 6
| 12 |  |  | 255
|  | 22 | S+6 |  | 3 | [6 empty] | 6
| 13 |  |  | 244
|  | 23 | S+0 |  |  | 6 | [5 empty] | 6
| 14 |  |  | 298
|  | 24 | M+0 |  |  |  |  | 6 |  |  |  | 3
| 22 | 31 | H+0 |  |  |  | 3 |  |  |  |  | 3
350
| 23 | 32 | S+0 |  |  | 6 | [5 empty] | 6
350
| 24 | 33 | S+3 |  | 3 | [6 empty] | 6
350
| 25 | 34 | S+3 |  | 3 | [6 empty] | 6
346
| 26 | 35 | S+0 |  |  | 6 | [5 empty] | 6
354
| 27 | 36 | S+3 |  | 3 | [6 empty] | 6
346
| 28 | 37 | S+0 |  |  | 6 | [5 empty] | 6
354
| 29 | 38 | S+0 |  | 3 | [6 empty] | 6
342
| 30 | 39 | S+6 |  | 3 | [6 empty] | 6
| 31 |  |  | 290
|  | 40 | S+0 |  |  | 6 | [5 empty] | 6
| 32 |  |  | 406
|  | 41 | S+6 |  | 3 | [6 empty] | 6
| 33 |  |  | 294
|  | 42 | S+3 |  | 3 | [6 empty] | 6
| 34 |  |  | 334
|  | 43 | S+3 |  |  | 6 | [5 empty] | 6
| 35 |  |  | 356
|  | 44 | S+0 |  | 3 | [6 empty] | 6
| 36 |  |  | 344
|  | 45 | S+0 |  | 3 | [6 empty] | 6
| 37 |  |  | 354
|  | 46 | S+3 |  | 3 | [6 empty] | 6
| 38 |  |  | 326
|  | 47 | S+0 |  | 3 | [6 empty] | 6
| 39 |  |  | 353
|  | 48 | H+0 |  |  |  | 3 | 6 |  |  |  | 6
| 40 |  |  | 370
| 41 | 49 | S+0 |  |  | 6 | [5 empty] | 6
330
| 42 | 50 | S+0 |  |  | 6 | [5 empty] | 6
350
| 43 | 51 | S+0 |  |  | 6 | [5 empty] | 6
350
| 44 | 52 | S+0 |  |  | 6 | [5 empty] | 6
351
| 45 | 53 | H+0 |  |  |  | 6 |  |  |  |  | 6
344
| 46 | 54 | S+0 |  | 3 | [6 empty] | 6
356
| 47 | 55 | L+3 |  |  |  |  | 12 |  |  |  | 9
480
| 48 | 56 | L+6 |  |  |  | 3 | 6 |  |  |  | 9
350
| 49 | 57 | S+0 |  | 3 | [6 empty] | 6
350
| 50 | 58 | S+0 |  | 3 | [6 empty] | 6
| 51 |  |  | 273
|  | 59 | S+0 |  | 3 | [6 empty] | 6
| 52 |  |  | 230
|  | 60 | S+3 |  |  | 6 | [5 empty] | 6
| 53 |  |  | 299.76
|  | 61 | L+6 |  |  |  | 3 | 6 |  |  |  | 9
| 54 |  |  | 475
|  | 62 | L+3 |  |  |  | 3 | 6 |  |  |  | 9
| 55 |  |  | 350
|  | 63 | S+3 |  | 3 | [6 empty] | 6
| 56 |  |  | 335
|  | 64 | S+3 |  |  | 6 | [5 empty] | 6
| 57 |  |  | 317
Appendix 1B:Page 3 of 6
| 58 | 65 | L+3 |  |  |  | 3 |  |  |  |  | 3
| 91 | 96 | L+3 |  |  |  |  | 6 |  |  |  | 6
415
| 92 | 97 | L+3 |  |  |  |  | 12 |  |  |  | 12
440
| 93 | 98 | L+6 |  |  |  | 3 | 6 |  |  |  | 9
393
| 94 | 99 | M+0 |  |  |  | 3 | 6 |  |  |  | 6
350
| 95 | 100 | S+9 |  | 3 | [6 empty] | 6
350
| 96 | 101 | S+0 |  | 3 | [6 empty] | 6
350
| 97 | 102 | S+9 |  | 3 | [6 empty] | 6
344
| 98 | 103 | S+0 |  | 3 | [6 empty] | 6
340
| 99 | 104 | S+6 |  |  | 6 | [5 empty] | 6
358
| 100 | 105 | S+0 |  |  | 6 | [5 empty] | 6
| 101 |  |  | 310
|  | 106 | S+0 |  | 3 | [6 empty] | 6
| 102 |  |  | 310
|  | 107 | S+0 |  |  | 6 | [5 empty] | 6
| 103 |  |  | 350
|  | 108 | S+6 |  |  | 6 | [5 empty] | 6
| 104 |  |  | 309
|  | 109 | M+3 |  |  |  |  | 6 |  |  |  | 3
| 158 | 160 | M+0 |  |  |  |  | 6 |  |  |  | 3
296.88
| 159 | 161 | S+0 |  | 3 | [6 empty] | 6
320
| 160 | 162 | S+3 |  |  | 6 | [5 empty] | 6
| 161 |  |  | 346
| 162 | 163 | S+3 | 332 |  | 6 | [5 empty] | 6
| 163 | 164 | S+0 | 301.4 | 3 | [6 empty] | 6
| 164 | 165 | L+0 | 380 |  |  | 6 |  |  |  |  | 6
| 165 | 166 | S+0 | 339 | 3 | [6 empty] | 6
| 166 | 167 | S+3 | 334 | 3 | [6 empty] | 6
| 167 | 168 | S+0 | 362 | 3 | [6 empty] | 6
| 168 | 169 | S+0 | 330 | 3 | [6 empty] | 6
| 169 | 170 | S+0 | 360 | 3 | [6 empty] | 6
| 170 | 171 | S+0 | 336 | 3 | [6 empty] | 6
171
|  | 172 | L+0 | 350 |  |  | 6 |  |  |  |  | 6
172
|  | 173 | S+0 | 350 | 3 | [6 empty] | 6
173
|  | 174 | S+0 | 300 | 3 | [6 empty] | 6
174
|  | 175 | S+3 | 339 | 3 | [6 empty] | 6
175
|  | 176 | S+0 | 330 | 3 | [6 empty] | 6
176
|  | 177 | S+0 | 304 | 3 | [6 empty] | 6
177
|  | 178 | S+0 | 332 | 3 | [6 empty] | 6
178
|  | 179 | S+0 | 350 |  | 6 | [5 empty] | 6
179
|  | 180 | L+0 |  |  |  |  | 6 |  |  |  | 3
|  | 193 | L+0 |  |  |  | 3 |  |  |  |  | 3
| 182 |  |  | 330
|  | 194 | S+0 |  | 3 | [6 empty] | 6
| 183 |  |  | 340
|  | 195 | S+0 |  | 3 | [6 empty] | 6
| 184 |  |  | 300
|  | 196 | S+0 |  | 3 | [6 empty] | 6
| 185 |  |  | 400
|  | 197 | S+0 |  |  | 6 | [5 empty] | 6
| 186 |  |  | 318
|  | 198 | S+0 |  |  | 6 | [5 empty] | 6
| 187 |  |  | 332.362
|  | 199 | S+0 |  | 3 | [6 empty] | 6
| 188 |  |  | 391
|  | 200 | L+6 |  |  |  |  | 12 |  |  |  | 6
| 189 |  |  | 345.714
|  | 201 | L+0 |  |  |  | 6 |  |  |  |  | 6
190
| 191 | 202 | S+0 |  | 3 | [6 empty] | 6
| SUMMARY SUB- TOTALS |  |  |  | 123 | 132 | 60 | 102 | 0 | 0 | 0 | 513 | 0
[8 empty] | TOTAL REQUIRED |  |  |  | ISSUED BY KETRACO
[5 empty] | 132KV INSULATORS FOR SINGLE CCT |  |  | 417 |  |  |  | 325
[5 empty] | BALANCE TO PROCURE |  |  | 92

## LYNX CONDUCTOR ACCESSORIES
CONTRACT FOR COMPLETION OF NANYUKI - ISIOLO 132KV TRANSMISSION LINE: KETRACO/PT/007/2021 CLIENT: KETRACO CONTRACTOR: BURHANI ENGINEERS LIMITED DOCUMENT NAME: APPENDIX 1B REV 1 CONDUCTOR HARDWARE FITTINGS SHORTAGE TOWER WISE DETAILS
13.11.2023
CONDUCTOR HARDWARE FITTINGS DETAILS
SL. No. | Tower No. | Tower Type |  | Hardware fittings
|  |  | SPAN AHEAD | Single Suspension String | Double Suspension String | Single Tension String | Double Tension String | V String | Jumper String
|  |  | METRES | Sets | Sets | Sets | Sets | Sets | Sets
1 | GANTRY | GANTRY |  | Sets: 9
28
2 | 1 | 3HT |  | Sets: 18; Sets: 9
209
3 | 2 | 3HT |  | Sets: 18; Sets: 9
325
4 | 3 | 3S |  | Sets: 3; Sets: 6
322
5 | 4 | 3S |  | Sets: 3; Sets: 6
338
6 | 5 | 3S |  | Sets: 3; Sets: 6
328
7 | 6 | 3S |  | Sets: 3; Sets: 6
295.5
8 | 7 | 3HT |  | Sets: 9
|  |  | 1845.5 | 6 | 6 | 54 | 0 | 24 | 18
10 | 21 | H+0 |  | Sets: 3
245
11 | 21A | S+3 |  | Sets: 3
192
12 | 21B | M+0 |  | Sets: 6
255
13 | 22 | S+6 |  | Sets: 3
244
14 | 23 | S+0 |  | Sets: 3
298
15 | 24 | M+0 |  | Sets: 3
22 | 31 | H+0 |  | Sets: 3
350
23 | 32 | S+0 |  | Sets: 3
350
24 | 33 | S+3 |  | Sets: 3
350
25 | 34 | S+3 |  | Sets: 3
346
26 | 35 | S+0 |  | Sets: 3
354
27 | 36 | S+3 |  | Sets: 3
346
28 | 37 | S+0 |  | Sets: 3
354
29 | 38 | S+0 |  | Sets: 3
342
30 | 39 | S+6 |  | Sets: 3
290
31 | 40 | S+0 |  | Sets: 3
406
32 | 41 | S+6 |  | Sets: 3
294
33 | 42 | S+3 |  | Sets: 3
334
34 | 43 | S+3 |  | Sets: 3
356
35 | 44 | S+0 |  | Sets: 3
344
36 | 45 | S+0 |  | Sets: 3
354
37 | 46 | S+3 |  | Sets: 3
326
38 | 47 | S+0 |  | Sets: 3
353
39 | 48 | H+0 |  | Sets: 3; Sets: 3
370
40 | 49 | S+0 |  | Sets: 3
330
41 | 50 | S+0 |  | Sets: 3
350
42 | 51 | S+0 |  | Sets: 3
350
43 | 52 | S+0 |  | Sets: 3
351
44 | 53 | H+0 |  | Sets: 6
344
45 | 54 | S+0 |  | Sets: 3
356
46 | 55 | L+3 |  | Sets: 6
480
47 | 56 | L+6 |  | Sets: 3; Sets: 3
350
48 | 57 | S+0 |  | Sets: 3
350
49 | 58 | S+0 |  | Sets: 3
273
50 | 59 | S+0 |  | Sets: 3
230
51 | 60 | S+3 |  | Sets: 3
299.76
52 | 61 | L+6 |  | Sets: 3; Sets: 3
475
53 | 62 | L+3 |  | Sets: 3; Sets: 3
350
54 | 63 | S+3 |  | Sets: 3
335
55 | 64 | S+3 |  | Sets: 3
317
Appendix 1B:Page 3 of 6
56 | 65 | L+3 |  | Sets: 3
87 | 96 | L+3 |  | Sets: 3
415
88 | 97 | L+3 |  | Sets: 6
440
89 | 98 | L+6 |  | Sets: 3; Sets: 3
393
90 | 99 | M+0 |  | Sets: 3; Sets: 3
350
91 | 100 | S+9 |  | Sets: 3
350
92 | 101 | S+0 |  | Sets: 3
350
93 | 102 | S+9 |  | Sets: 3
344
94 | 103 | S+0 |  | Sets: 3
340
95 | 104 | S+6 |  | Sets: 3
358
96 | 105 | S+0 |  | Sets: 3
310
97 | 106 | S+0 |  | Sets: 3
310
98 | 107 | S+0 |  | Sets: 3
350
99 | 108 | S+6 |  | Sets: 3
309
100 | 109 | M+3 |  | Sets: 3
151 | 160 | M+0 |  | Sets: 3
296.88
152 | 161 | S+0 |  | Sets: 3
320
153 | 162 | S+3 |  | Sets: 3
346
154 | 163 | S+3 | 332 | Sets: 3
155 | 164 | S+0 | 301.4 | Sets: 3
156 | 165 | L+0 | 380 | Sets: 6
157 | 166 | S+0 | 339 | Sets: 3
158 | 167 | S+3 | 334 | Sets: 3
159 | 168 | S+0 | 362 | Sets: 3
160 | 169 | S+0 | 330 | Sets: 3
161 | 170 | S+0 | 360 | Sets: 3
162 | 171 | S+0 | 336 | Sets: 3
163 | 172 | L+0 | 350 | Sets: 6
164 | 173 | S+0 | 350 | Sets: 3
165 | 174 | S+0 | 300 | Sets: 3
166 | 175 | S+3 | 339 | Sets: 3
167 | 176 | S+0 | 330 | Sets: 3
168 | 177 | S+0 | 304 | Sets: 3
169 | 178 | S+0 | 332 | Sets: 3
170 | 179 | S+0 | 350 | Sets: 3
171 | 180 | L+0 |  | Sets: 3
172 | 193 | L+0 |  | Sets: 3
330
173 | 194 | S+0 |  | Sets: 3
340
174 | 195 | S+0 |  | Sets: 3
300
175 | 196 | S+0 |  | Sets: 3
400
176 | 197 | S+0 |  | Sets: 3
318
177 | 198 | S+0 |  | Sets: 3
332.362
178 | 199 | S+0 |  | Sets: 3
391
179 | 200 | L+6 |  | Sets: 6
345.714
180 | 201 | L+0 |  | Sets: 6
181 | 202 | S+0 |  | Sets: 3
SUMMARY SUB- TOTALS |  |  |  | 123 | 66 | 60 | 51 | 0 | 0
ISSUED BY KETRACO |  |  |  | 120 | 20 | 63 | 51 | 0 | 0
BALANCE |  |  |  | 3 | 46 | -3 | 0 |  | 0
|  |  |  | 41 | 22 | 15 | 14 | 0 | 0
[6 empty] | 10 ONE SIDE | 11 ONE SIDE
[6 empty] | 5 DOUBLE | 3 DOUBLE

## SUMMARY
| SINGLE SUSPENSION STRING ASSEMBLY 123 SETS | QUANTITIES FOR EACH SET | NEEDED QUANTITIES | ISSUED BY KETRACO | BALANCE | available in Ketraco store | To procurement
1 | STRAIGHT SHACKLE GN - 16T | 1 | 123 | 120 | 3 | 3 | 0
2 | BALL EYE ABC-16-P | 1 | 123 | 120 | 3 | 3 | 0
3 | ARCHING HORN DC-35/19 | 2 | 246 | 120 | 126 | 126 | 0
4 | BALL SOCKET RC -16-P/36 | 1 | 123 | 120 | 3 | 3 | 0
5 | ARCHING HORN DC-35/11 | 2 | 246 | 120 | 126 | 126 | 0
6 | SUSPENSION CLAMP GST -5 | 1 | 123 | 120 | 3 | 3 | 0
7 | ARMOR RODS VPAL - 188-199/D | 1 | 123 | 120 | 3 | 3 | 0
| DOUBLE SUSPENSION STRINGASSEMBLY 66 SETS | QUANTITIES | NEEDED QUANTITIES | ISSUED BY KETRACO | BALANCE | available in Ketraco store | To procurement
1 | STRAIGHT SHACKLE GN-16T | 2 | 132 | 40 | 92 | 92 | 0
2 | CHAIN LINK ES-16/20 | 1 | 66 | 20 | 46 | 0 | 46
3 | TRIANGULAR YOKE Y-16/400-14 | 2 | 132 | 40 | 92 | 42 | 50
4 | ARCHING HORN DI-35/19 | 2 | 132 | 40 | 92 | 4 | 88
5 | BALL CLEVIS HPB-16 | 2 | 132 | 40 | 92 | 0 | 92
6 | CLEVIS SOCKET RH-16 | 2 | 132 | 40 | 92 | 62 | 30
7 | ARCHING HORN DI-35/13 | 2 | 132 | 40 | 92 | 3 | 89
8 | CLEVIS EYE HR-16/45 | 1 | 66 | 20 | 46 | 46 | 0
9 | SUSPENSION CLAMP GST - 5 | 1 | 66 | 20 | 46 | 46 | 0
10 | ARMOR RODS VPAL-188-199/D | 1 | 66 | 20 | 46 | 46 | 0
| SINGLE TENSION STRING ASSEMBLY 63 SETS | QUANTITIES | NEEDED QUANTITIES | ISSUED BY KETRACO | BALANCE |  | To procurement
1 | STRAIGHT SHACKLE GN - 16T | 1 | 63 | 63 | 0 |  | 0
2 | BALL EYE ABC-16-P | 1 | 63 | 63 | 0 |  | 0
3 | ARCHING HORN DC-35/19 | 1 | 63 | 63 | 0 |  | 0
4 | ARCHING HORN DC-35/11 | 1 | 63 | 63 | 0 |  | 0
5 | SOCKET EYE RC -16-P/21 | 1 | 63 | 63 | 0 |  | 0
6 | JUMPER TERMINAL DC-38.5 | 1 | 63 | 63 | 0 |  | 0
7 | COMPRESSION CLAMP CH-226 C/W EYE TERMINAL | 1 | 63 | 63 | 0 |  | 0
| DOUBLE TENSION STRING ASSEMBLY 51SETS | QUANTITIES | NEEDED QUANTITIES | ISSUED BY KETRACO | BALANCE |  | To procurement
1 | STRAIGHT SHACKLE GN-16T | 2 | 102 | 102 | 0 |  | 0
2 | CHAIN LINK ES-16/20 | 1 | 51 | 51 | 0 |  | 0
3 | YOKE PLATE Y-16/400-14 | 2 | 102 | 102 | 0 |  | 0
4 | CLEVIS BALL HBP - 16 | 2 | 102 | 102 | 0 |  | 0
5 | CLEVIS SOCKET RH-16 | 2 | 102 | 102 | 0 |  | 0
6 | CLEVIS EYE HR-16/21 | 1 | 51 | 33 | 18 | 0 | 18
7 | JUMPER TERMINAL DC-38.5 | 1 | 51 | 51 | 0 |  | 0
8 | COMPRESSION CLAMP CH-226 C/W EYE TERMINAL | 1 | 51 | 51 | 0 |  | 0
9 | ARCHING HORN DI-35/19 | 1 | 51 | 51 | 0 |  | 0
10 | ARCHING HORN DI-35/13 | 1 | 51 | 51 | 0 |  | 0
TRIPLE CIRCUIT BOQ
| SINGLE SUSPENSION STRING ASSEMBLY 6 SETS | QUANTITIES | NEEDED QUANTITIES | ISSUED BY KETRACO | BALANCE |  | To procurement
1 | STRAIGHT SHACKLE GN - 16T | 1 | 6 | 0 | 6 | 6 | 0
2 | BALL EYE ABC-16-P | 1 | 6 | 0 | 6 | 6 | 0
3 | ARCHING HORN DC-35/19 | 2 | 12 | 0 | 12 | 12 | 0
4 | BALL SOCKET RC -16-P/36 | 1 | 6 | 0 | 6 | 6 | 0
5 | ARCHING HORN DC-35/11 | 2 | 12 | 0 | 12 | 12 | 0
6 | SUSPENSION CLAMP GST -5 | 1 | 6 | 0 | 6 | 6 | 0
7 | ARMOR RODS VPAL - 188-199/D | 1 | 6 | 0 | 6 | 6 | 0
| SINGLE TENSION STRING ASSEMBLY 54 SETS | QUANTITIES | NEEDED QUANTITIES | ISSUED BY KETRACO | BALANCE |  | To procurement
1 | STRAIGHT SHACKLE GN - 16T | 1 | 54 | 0 | 54 | 54 | 0
2 | BALL EYE ABC-16-P | 1 | 54 | 0 | 54 | 54 | 0
3 | ARCHING HORN DC-35/19 | 1 | 54 | 0 | 54 | 54 | 0
4 | ARCHING HORN DC-35/11 | 1 | 54 | 0 | 54 | 54 | 0
5 | SOCKET EYE RC -16-P/21 | 1 | 54 | 0 | 54 | 51 | 3
6 | JUMPER TERMINAL DC-38.5 | 1 | 54 | 0 | 54 | 47 | 0
7 | COMPRESSION CLAMP CH-226 C/W EYE TERMINAL | 1 | 54 | 0 | 54 | 54 | 0
| DOUBLE SUSPENSION STRINGASSEMBLY 6SETS | QUANTITIES | NEEDED QUANTITIES | ISSUED BY KETRACO | BALANCE |  | To procurement
1 | STRAIGHT SHACKLE GN-16T | 2 | 12 | 0 | 12 | 12 | 0
2 | CHAIN LINK ES-16/20 | 1 | 6 | 0 | 6 | 0 | 6
3 | TRIANGULAR YOKE Y-16/400-14 | 2 | 12 | 0 | 12 | 0 | 12
4 | ARCHING HORN DI-35/19 | 2 | 12 | 0 | 12 | 0 | 12
5 | BALL CLEVIS HPB-16 | 2 | 12 | 0 | 12 | 0 | 12
6 | CLEVIS SOCKET RH-16 | 2 | 12 | 0 | 12 | 0 | 12
7 | ARCHING HORN DI-35/13 | 2 | 12 | 0 | 12 | 0 | 12
8 | CLEVIS EYE HR-16/45 | 1 | 6 | 0 | 6 | 0 | 6
9 | SUSPENSION CLAMP GST - 5 | 1 | 6 | 0 | 6 | 6 | 0
10 | ARMOR RODS VPAL-188-199/D | 1 | 6 | 0 | 6 | 6 | 0
| V SUSPENSION STRING ASSEMBLY 24 SETS | QUANTITIES | NEEDED QUANTITIES | ISSUED BY KETRACO | BALANCE |  | To procurement
1 | STRAIGHT SHACKLE GN-16T | 2 | 48 | 0 | 48 | 48 | 0
2 | BALL EYE ABC-16-P | 2 | 48 | 0 | 48 | 48 | 0
3 | TRIANGULAR YOKE Y-16/400-14 | 1 | 24 | 0 | 24 | 0 | 24
4 | ARCHING HORN DI-35/19 | 2 | 48 | 0 | 48 | 0 | 48
5 | CLEVIS SOCKET RH-16 | 2 | 48 | 0 | 48 | 0 | 48
6 | ARCHING HORN DI-35/13 | 2 | 48 | 0 | 48 | 0 | 48
7 | CLEVIS EYE HR-16/45 | 1 | 24 | 0 | 24 | 0 | 24
8 | SUSPENSION CLAMP GST - 5 | 1 | 24 | 0 | 24 | 24 | 0
9 | ARMOR RODS VPAL-188-199/D | 1 | 24 | 0 | 24 | 24 | 0
| JUMPER STRING ASSEMBLY 18 SETS | QUANTITIES | NEEDED QUANTITIES | ISSUED BY KETRACO | BALANCE |  | To procurement
1 | JUMPER TERMINAL DC-38.5 | 2 | 36 | 0 | 36 | 0 | 36
2 | STRAIGHT SHACKLE GN - 16T | 1 | 18 | 0 | 18 | 18 | 0
3 | BALL EYE ABC-16-P | 1 | 18 | 0 | 18 | 18 | 0
4 | BALL SOCKET RC -16-P/36 | 1 | 18 | 0 | 18 | 0 | 18
5 | SUSPENSION CLAMP GST -5 | 1 | 18 | 0 | 18 | 18 | 0
6 | ARMOR RODS VPAL - 188-199/D | 1 | 18 | 0 | 18 | 18 | 0
| OTHER CONDUCTOR ACCESSORIES |  | REQUIRED QUANTITIES | ISSUED BY KETRACO
1 | VIBRATION DAMPERS 513 pcs singel and 117 pcs for multi |  | 630 | 558 |  | 0 | 72
2 | VIBRATION DAMPERS ARMOR RODS 513 pcs singel and 117 pcs for multi |  | 630 |  |  |  | 630 | Available amour Rods VPAL 188-199/D 64pcs at ketraco
Insulators
1 | 132KV insulator for singel circuit |  | 417 | 325 |  | 92 | 0
2 | 132KV insulator for multi circuits |  | 138 | 0 |  | 133 | 5
3 | 132KV Jumper insulator multi circuit |  | 18 |  |  | 0 | 18
4 | 132KV insulator for singel circuit for replacing damaged insulators |  | 10 |  |  | 0 | 10
Others
1 | Number Plate |  | 194 |  |  | 205 | 0
2 | Danger Plate |  | 388 |  |  | 257 | 131
3 | Warning atsphere |  | ? |  |  | 60 | 0
4 | Phase Plate |  | 0
OPGW FITTINGS
| Suspension Assembly needs 88 sets |  |  | 75 sets received
1 | D Sharkle GN-16 | 1 | 88 | 75 | 13 | 13 | 0
2 | Eye Chain lnk FSR- 16A | 1 | 88 | 75 | 13 | 13 | 0
3 | AGS Clamp (suspension) GAS -3 | 1 | 88 | 75 | 13 | 13 | 0
4 | Amrod rod of OPGW VPG 53AL-FL.15.D | 1 | 88 | 75 | 13 | 13 | 0
5 | Parallel clamp GPC-11-30 | 1 | 88 | 75 | 13 | 8 | 5
6 | Single tower clamp GCSAL 14-18 | 1 | 88 | 75 | 13 | 13 | 0
OPGW accessaries
7 | Vibraation Damper of OPGW 18-26 |  | 315 | 280 | 35 | 0 | 35
8 | Damper protection Armour rods (boudle) VPAW FO 15/1/800 | 1 | 315 | 88 | 227 | 0 | 227
| Tension Assemly for passsing Through 34 sets |  |  | 29 sets received
1 | D Sharkle GN-16 | 2 | 68 | 58 | 10 | 10 | 0
2 | Extension Links TA-1/300 | 1 | 34 | 29 | 5 | 5 | 0
3 | Thimble G-16 | 1 | 34 | 29 | 5 | 5 | 0
4 | Protection Splice EPAW- FO-15/1/2600 | 3 | 102 | 116 | -14 | 22(4 in each Bundle) Available | 0
5 | Dead end (Gripper) RAAW FO 21.50/Dcha | 1 | 34 | 29 | 5 | 0 | 5
6 | Single Tower Clamp GCSAL 14-18 | 1 | 34 | 29 | 5 | 5 | 0
Tension Assemly for Joint box 30 sets
1 | D Sharkle GN-16 | 2 | 60 | 58 | 2 | 2 | 0
2 | Extension Links TA-1/300 | 1 | 30 | 29 | 1 | 1 | 0
3 | Thimble G-16 | 1 | 30 | 29 | 1 | 1 | 0
4 | Protection Splice EPAW- FO-15/1/2600 | 1 | 30 | 29 | 1 | 0 | 1
5 | Dead end (Gripper) RAAW FO 21.50/Dcha | 1 | 30 | 29 | 1 | 0 | 1
6 | Single Tower Clamp GCSAL 14-18 | 1 | 30 | 29 | 1 | 1 | 0
7 | Joint Box |  |  | 19
8 | Down lead Clamp SFO-CD-3 |  | 324 | 309 | 15 | 15 | 0

## Sheet1
SINGLE SUSPENSION STRING ASSEMBLY 123 SETS | QUANTITIES FOR EACH SET | NEEDED QUANTITIES | ISSUED BY KETRACO | BALANCE | available in Ketraco store | To procurement | 0 | 0
STRAIGHT SHACKLE GN - 16T | 1 | 123 | 120 | 3 | 3 | 0 | 0 | 0
BALL EYE ABC-16-P | 1 | 123 | 120 | 3 | 3 | 0 | 0 | 0
ARCHING HORN DC-35/19 | 2 | 246 | 120 | 126 | 126 | 0 | 0 | 0
BALL SOCKET RC -16-P/36 | 1 | 123 | 120 | 3 | 3 | 0 | 0 | 0
ARCHING HORN DC-35/11 | 2 | 246 | 120 | 126 | 126 | 0 | 0 | 0
SUSPENSION CLAMP GST -5 | 1 | 123 | 120 | 3 | 3 | 0 | 0 | 0
ARMOR RODS VPAL - 188-199/D | 1 | 123 | 120 | 3 | 3 | 0 | 0 | 0
STRAIGHT SHACKLE GN-16T | 2 | 132 | 40 | 92 | 92 | 0 | 0 | 0
CHAIN LINK ES-16/20 | 1 | 66 | 20 | 46 | 0 | 46 | 0 | 0
TRIANGULAR YOKE Y-16/400-14 | 2 | 132 | 40 | 92 | 42 | 50 | 0 | 0
ARCHING HORN DI-35/19 | 2 | 132 | 40 | 92 | 4 | 88 | 0 | 0
BALL CLEVIS HPB-16 | 2 | 132 | 40 | 92 | 0 | 92 | 0 | 0
CLEVIS SOCKET RH-16 | 2 | 132 | 40 | 92 | 62 | 30 | 0 | 0
ARCHING HORN DI-35/13 | 2 | 132 | 40 | 92 | 3 | 89 | 0 | 0
CLEVIS EYE HR-16/45 | 1 | 66 | 20 | 46 | 46 | 0 | 0 | 0
SUSPENSION CLAMP GST - 5 | 1 | 66 | 20 | 46 | 46 | 0 | 0 | 0
ARMOR RODS VPAL-188-199/D | 1 | 66 | 20 | 46 | 46 | 0 | 0 | 0
STRAIGHT SHACKLE GN - 16T | 1 | 63 | 63 | 0 | 0 | 0 | 0 | 0
BALL EYE ABC-16-P | 1 | 63 | 63 | 0 | 0 | 0 | 0 | 0
ARCHING HORN DC-35/19 | 1 | 63 | 63 | 0 | 0 | 0 | 0 | 0
ARCHING HORN DC-35/11 | 1 | 63 | 63 | 0 | 0 | 0 | 0 | 0
SOCKET EYE RC -16-P/21 | 1 | 63 | 63 | 0 | 0 | 0 | 0 | 0
JUMPER TERMINAL DC-38.5 | 1 | 63 | 63 | 0 | 0 | 0 | 0 | 0
COMPRESSION CLAMP CH-226 C/W EYE TERMINAL | 1 | 63 | 63 | 0 | 0 | 0 | 0 | 0
STRAIGHT SHACKLE GN-16T | 2 | 102 | 102 | 0 | 0 | 0 | 0 | 0
CHAIN LINK ES-16/20 | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 0
YOKE PLATE Y-16/400-14 | 2 | 102 | 102 | 0 | 0 | 0 | 0 | 0
CLEVIS BALL HBP - 16 | 2 | 102 | 102 | 0 | 0 | 0 | 0 | 0
CLEVIS SOCKET RH-16 | 2 | 102 | 102 | 0 | 0 | 0 | 0 | 0
CLEVIS EYE HR-16/21 | 1 | 51 | 33 | 18 | 0 | 18 | 0 | 0
JUMPER TERMINAL DC-38.5 | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 0
COMPRESSION CLAMP CH-226 C/W EYE TERMINAL | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 0
ARCHING HORN DI-35/19 | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 0
ARCHING HORN DI-35/13 | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 0
STRAIGHT SHACKLE GN - 16T | 1 | 6 | 0 | 6 | 6 | 0 | 0 | 0
BALL EYE ABC-16-P | 1 | 6 | 0 | 6 | 6 | 0 | 0 | 0
ARCHING HORN DC-35/19 | 2 | 12 | 0 | 12 | 12 | 0 | 0 | 0
BALL SOCKET RC -16-P/36 | 1 | 6 | 0 | 6 | 6 | 0 | 0 | 0
ARCHING HORN DC-35/11 | 2 | 12 | 0 | 12 | 12 | 0 | 0 | 0
SUSPENSION CLAMP GST -5 | 1 | 6 | 0 | 6 | 6 | 0 | 0 | 0
ARMOR RODS VPAL - 188-199/D | 1 | 6 | 0 | 6 | 6 | 0 | 0 | 0
STRAIGHT SHACKLE GN - 16T | 1 | 54 | 0 | 54 | 54 | 0 | 0 | 0
BALL EYE ABC-16-P | 1 | 54 | 0 | 54 | 54 | 0 | 0 | 0
ARCHING HORN DC-35/19 | 1 | 54 | 0 | 54 | 54 | 0 | 0 | 0
ARCHING HORN DC-35/11 | 1 | 54 | 0 | 54 | 54 | 0 | 0 | 0
SOCKET EYE RC -16-P/21 | 1 | 54 | 0 | 54 | 51 | 3 | 0 | 0
JUMPER TERMINAL DC-38.5 | 1 | 54 | 0 | 54 | 47 | 0 | 0 | 0
COMPRESSION CLAMP CH-226 C/W EYE TERMINAL | 1 | 54 | 0 | 54 | 54 | 0 | 0 | 0
STRAIGHT SHACKLE GN-16T | 2 | 12 | 0 | 12 | 12 | 0 | 0 | 0
CHAIN LINK ES-16/20 | 1 | 6 | 0 | 6 | 0 | 6 | 0 | 0
TRIANGULAR YOKE Y-16/400-14 | 2 | 12 | 0 | 12 | 0 | 12 | 0 | 0
ARCHING HORN DI-35/19 | 2 | 12 | 0 | 12 | 0 | 12 | 0 | 0
BALL CLEVIS HPB-16 | 2 | 12 | 0 | 12 | 0 | 12 | 0 | 0
CLEVIS SOCKET RH-16 | 2 | 12 | 0 | 12 | 0 | 12 | 0 | 0
ARCHING HORN DI-35/13 | 2 | 12 | 0 | 12 | 0 | 12 | 0 | 0
CLEVIS EYE HR-16/45 | 1 | 6 | 0 | 6 | 0 | 6 | 0 | 0
SUSPENSION CLAMP GST - 5 | 1 | 6 | 0 | 6 | 6 | 0 | 0 | 0
ARMOR RODS VPAL-188-199/D | 1 | 6 | 0 | 6 | 6 | 0 | 0 | 0
STRAIGHT SHACKLE GN-16T | 2 | 48 | 0 | 48 | 48 | 0 | 0 | 0
BALL EYE ABC-16-P | 2 | 48 | 0 | 48 | 48 | 0 | 0 | 0
TRIANGULAR YOKE Y-16/400-14 | 1 | 24 | 0 | 24 | 0 | 24 | 0 | 0
ARCHING HORN DI-35/19 | 2 | 48 | 0 | 48 | 0 | 48 | 0 | 0
CLEVIS SOCKET RH-16 | 2 | 48 | 0 | 48 | 0 | 48 | 0 | 0
ARCHING HORN DI-35/13 | 2 | 48 | 0 | 48 | 0 | 48 | 0 | 0
CLEVIS EYE HR-16/45 | 1 | 24 | 0 | 24 | 0 | 24 | 0 | 0
SUSPENSION CLAMP GST - 5 | 1 | 24 | 0 | 24 | 24 | 0 | 0 | 0
ARMOR RODS VPAL-188-199/D | 1 | 24 | 0 | 24 | 24 | 0 | 0 | 0
JUMPER TERMINAL DC-38.5 | 2 | 36 | 0 | 36 | 0 | 36 | 0 | 0
STRAIGHT SHACKLE GN - 16T | 1 | 18 | 0 | 18 | 18 | 0 | 0 | 0
BALL EYE ABC-16-P | 1 | 18 | 0 | 18 | 18 | 0 | 0 | 0
BALL SOCKET RC -16-P/36 | 1 | 18 | 0 | 18 | 0 | 18 | 0 | 0
SUSPENSION CLAMP GST -5 | 1 | 18 | 0 | 18 | 18 | 0 | 0 | 0
ARMOR RODS VPAL - 188-199/D | 1 | 18 | 0 | 18 | 18 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Backstay
Backstays materials |  |  | 1 stay | 203# | 193# | 180# | 160# | 154# | 110 | 109# | 96# | 65# | 31# | 24# | Summary | 11 Towers
No | Decription | Unit | Qty | [12 empty] | Qty
|  |  |  | 4 | 3 | 3 | 3 | 1 | 1 | 3 | 4 | 4 | 4 | 4
1 | 16mm dia galvanized steel wire rope | Meters | 40 | 160 | 120 | 120 | 120 | 40 | 40 | 120 | 160 | 160 | 160 | 160 | 1360 | 2720
2 | D shackle above 3T | Pcs | 2 | 8 | 6 | 6 | 6 | 2 | 2 | 6 | 8 | 8 | 8 | 8 | 68 | 68
3 | 3/4'' U clamps | Pcs | 12 | 48 | 36 | 36 | 36 | 12 | 12 | 36 | 48 | 48 | 48 | 48 | 408 | 408
4 | 2 mtr CCA treated logs of around 200mm dia | Pcs | 2 | 8 | 6 | 6 | 6 | 2 | 2 | 6 | 8 | 8 | 8 | 8 | 68 | 68
this list shows backstay we need to do replacement to existing backstay
Avaverlheight of cross arm 24m, steel rope= 24m*1.5+2m+2m=40m
this list doesn't include of backstay for new stringing
Backstay of tower 203# will shift to tower 65#

## Earthing
Earthing kit materials |  |  |  | 1 tower has 2 sets of Earthing Kit | 5# | 21# | 21A# | 21B# | 60# | 98# | 165# | 166# | 167# | 178# | 198# | 199# | 200# | 201# | Summary
No | Decription | Sepcification | Unit | Qty for each kit
[5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
1 | Ground Rod | Φ20mm galvanized steel L3000mm (min) | Pcs | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 28
2 | Counterpoise | Φ11.5mm galvanized steel wire | m | 1 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 322
3 | Clamps | Dip gavernized and suiable for Φ11.5mm gavernized wire, with anthi theft bolts 2nos M12 | Pcs | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 28
4 | Typical connection between counterpoise and Ground rod |  | Pcs | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 2 | 34
5 | Typical connection between counterpoises ( extension) | Optional | Pcs | 1 | [10 empty] | 2 | 2 | 2 |  | 6
6 | Counterpoise for extension | Optional | Pcs | 1 | [10 empty] | 22 | 22 | 22 |  | 66

## DOABLE SCOPE loc 31_65
CONTRACT FOR COMPLETION OF NANYUKI - ISIOLO 132KV TRANSMISSION LINE: KETRACO/PT/007/2021 CLIENT: KETRACO CONTRACTOR: BURHANI ENGINEERS LIMITED DOCUMENT NAME: APPENDIX 1B REV 1 CONDUCTOR HARDWARE FITTINGS SHORTAGE TOWER WISE DETAILS
DATE. 13TH NOV, 2023
CONDUCTOR HARDWARE FITTINGS DETAILS
SL. No. | Tower No. | Tower Type |  | Insulator |  |  |  | Hardware fittings |  |  |  | Conductor Accesorries
|  |  | SPAN AHEAD | Single Suspension Insulator | Double Suspension Insulator | Single Tension Insulator | Double Tension Insulator | Single Suspension String | Double Suspension String | Single Tension String | Double Tension String | Midspan Joints | Vibration Damper | Repair Sleeve | Jumper Cone | Compression Clamp (Dead End) Aluminium
|  |  | METRES | Nos. | Nos. | Nos. | Nos. | Sets | Sets | Sets | Sets | Sets | Nos. | Nos. | Nos | Nos
SUMMARY TOTALS |  |  | 11759.76 | 48 | 66 | 24 | 36 | 48 | 33 | 24 | 18 | 0 | 216 | 0 | 42 | 42
22 | 31 | H+0 |  |  |  | 3 |  |  |  | 3 |  |  | 3 |  | 6 | 3
350
23 | 32 | S+0 |  |  | 6 |  |  |  | 3 |  |  |  | 6
350
24 | 33 | S+3 |  | 3 |  |  |  | 3 |  |  |  |  | 6
350
25 | 34 | S+3 |  | 3 |  |  |  | 3 |  |  |  |  | 6
346
26 | 35 | S+0 |  |  | 6 |  |  |  | 3 |  |  |  | 6
354
27 | 36 | S+3 |  | 3 |  |  |  | 3 |  |  |  |  | 6
346
28 | 37 | S+0 |  |  | 6 |  |  |  | 3 |  |  |  | 6
354
29 | 38 | S+0 |  | 3 |  |  |  | 3 |  |  |  |  | 6
342
30 | 39 | S+6 |  | 3 |  |  |  | 3 |  |  |  |  | 6
290
31 | 40 | S+0 |  |  | 6 |  |  |  | 3 |  |  |  | 6
406
32 | 41 | S+6 |  | 3 |  |  |  | 3 |  |  |  |  | 6
294
33 | 42 | S+3 |  | 3 |  |  |  | 3 |  |  |  |  | 6
334
34 | 43 | S+3 |  |  | 6 |  |  |  | 3 |  |  |  | 6
356
35 | 44 | S+0 |  | 3 |  |  |  | 3 |  |  |  |  | 6
344
36 | 45 | S+0 |  | 3 |  |  |  | 3 |  |  |  |  | 6
354
37 | 46 | S+3 |  | 3 |  |  |  | 3 |  |  |  |  | 6
326
38 | 47 | S+0 |  | 3 |  |  |  | 3 |  |  |  |  | 6
353
39 | 48 | H+0 |  |  |  | 3 | 6 |  |  | 3 | 3 |  | 6 |  | 6 | 6
370
40 | 49 | S+0 |  |  | 6 |  |  |  | 3 |  |  |  | 6
330
41 | 50 | S+0 |  |  | 6 |  |  |  | 3 |  |  |  | 6
350
42 | 51 | S+0 |  |  | 6 |  |  |  | 3 |  |  |  | 6
350
43 | 52 | S+0 |  |  | 6 |  |  |  | 3 |  |  |  | 6
351
44 | 53 | H+0 |  |  |  | 6 |  |  |  | 6 |  |  | 6 |  | 6 | 6
344
45 | 54 | S+0 |  | 3 |  |  |  | 3 |  |  |  |  | 6
356
46 | 55 | L+3 |  |  |  |  | 12 |  |  |  | 6 |  | 9 |  | 6 | 6
480
47 | 56 | L+6 |  |  |  | 3 | 6 |  |  | 3 | 3 |  | 9 |  | 6 | 6
350
48 | 57 | S+0 |  | 3 |  |  |  | 3 |  |  |  |  | 6
350
49 | 58 | S+0 |  | 3 |  |  |  | 3 |  |  |  |  | 6
273
50 | 59 | S+0 |  | 3 |  |  |  | 3 |  |  |  |  | 6
230
51 | 60 | S+3 |  |  | 6 |  |  |  | 3 |  |  |  | 6
299.76
52 | 61 | L+6 |  |  |  | 3 | 6 |  |  | 3 | 3 |  | 9 |  | 6 | 6
475
53 | 62 | L+3 |  |  |  | 3 | 6 |  |  | 3 | 3 |  | 9 |  | 6 | 6
350
54 | 63 | S+3 |  | 3 |  |  |  | 3 |  |  |  |  | 6
335
55 | 64 | S+3 |  |  | 6 |  |  |  | 3 |  |  |  | 6
317
56 | 65 | L+3 |  |  |  | 3 |  |  |  | 3 |  |  | 3 |  | 0 | 3
[7 empty] | REQUIRED QUANTITIES | ISSUED BY KETRACO
[5 empty] | INSULATORS NEEDED |  | 174 | 325
[5 empty] | SINGLE SUSPENSION STRING ASSEMBLY 48 SETS | PER SET | REQUIRED QUANTITIES | ISSUED BY KETRACO
|  |  |  | 1 | STRAIGHT SHACKLE GN - 16T | 1 | 48 | 120
|  |  |  | 2 | BALL EYE ABC-16-P | 1 | 48 | 120
|  |  |  | 3 | ARCHING HORN DC-35/19 | 2 | 96 | 120
|  |  |  | 4 | BALL SOCKET RC -16-P/36 | 1 | 48 | 120
|  |  |  | 5 | ARCHING HORN DC-35/11 | 2 | 96 | 120
|  |  |  | 6 | SUSPENSION CLAMP GST -5 | 1 | 48 | 120
|  |  |  | 7 | ARMOR RODS VPAL - 188-199/D | 1 | 48 | 120
[5 empty] | DOUBLE SUSPENSION STRINGASSEMBLY 33 SETS | PER SET | REQUIRED QUANTITIES | ISSUED BY KETRACO
|  |  |  | 1 | STRAIGHT SHACKLE GN-16T | 2 | 66 | 40
|  |  |  | 2 | CHAIN LINK ES-16/20 | 1 | 33 | 20
|  |  |  | 3 | TRIANGULAR YOKE Y-16/400-14 | 2 | 66 | 40
|  |  |  | 4 | ARCHING HORN DI-35/19 | 2 | 66 | 40
|  |  |  | 5 | BALL CLEVIS HPB-16 | 2 | 66 | 40
|  |  |  | 6 | CLEVIS SOCKET RH-16 | 2 | 66 | 40
|  |  |  | 7 | ARCHING HORN DI-35/13 | 2 | 66 | 40
|  |  |  | 8 | CLEVIS EYE HR-16/45 | 1 | 33 | 20
|  |  |  | 9 | SUSPENSION CLAMP GST - 5 | 1 | 33 | 20
|  |  |  | 10 | ARMOR RODS VPAL-188-199/D | 1 | 33 | 20
[5 empty] | SINGLE TENSION STRING ASSEMBLY 24 SETS | PER SET | REQUIRED QUANTITIES | ISSUED BY KETRACO
|  |  |  | 1 | STRAIGHT SHACKLE GN - 16T | 1 | 24 | 63
|  |  |  | 2 | BALL EYE ABC-16-P | 1 | 24 | 63
|  |  |  | 3 | ARCHING HORN DC-35/19 | 1 | 24 | 63
|  |  |  | 4 | ARCHING HORN DC-35/11 | 1 | 24 | 63
|  |  |  | 5 | SOCKET EYE RC -16-P/21 | 1 | 24 | 63
|  |  |  | 6 | JUMPER TERMINAL DC-38.5 | 1 | 24 | 63
|  |  |  | 7 | COMPRESSION CLAMP CH-226 C/W EYE TERMINAL | 1 | 24 | 63
[5 empty] | DOUBLE TENSION STRING ASSEMBLY 18 SETS | PER SET | REQUIRED QUANTITIES | ISSUED BY KETRACO
|  |  |  | 1 | STRAIGHT SHACKLE GN-16T | 2 | 36 | 102
|  |  |  | 2 | CHAIN LINK ES-16/20 | 1 | 18 | 51
|  |  |  | 3 | YOKE PLATE Y-16/400-14 | 2 | 36 | 102
|  |  |  | 4 | CLEVIS BALL HBP - 16 | 2 | 36 | 102
|  |  |  | 5 | CLEVIS SOCKET RH-16 | 2 | 36 | 102
|  |  |  | 6 | CLEVIS EYE HR-16/21 | 1 | 18 | 33
|  |  |  | 7 | JUMPER TERMINAL DC-38.5 | 1 | 18 | 51
|  |  |  | 8 | COMPRESSION CLAMP CH-226 C/W EYE TERMINAL | 1 | 18 | 51
|  |  |  | 9 | ARCHING HORN DI-35/19 | 1 | 18 | 51
|  |  |  | 10 | ARCHING HORN DI-35/13 | 1 | 18 | 51
[5 empty] | CONDUCTOR ACCESSORIES |  | REQUIRED QUANTITIES | ISSUED BY KETRACO
[5 empty] | VIBRATION DUMPERS |  | 216 | 558
[5 empty] | JUMPER TERMINAL DC 38.5 (JUMPER CONE) |  | 42 | 174